## Commercial Summary
Commercial Summary Schedule
Proposed subcontract departures – Harrow Street
VTX-HARROW-CSS-001 · Revision A · Prepared 18 September 2026 · For builder review
Project |  | Harrow Street |  | Trade Package | FC01 Facade Cladding Package
Project Address |  | 42 Harrow Street, Brunswick East, Victoria 3057 |  | Contract Type | Lump Sum – Supply and Install of FC01 Facade Cladding Package
Head Contractor |  | Northline Constructions (Vic) Pty Ltd (ACN 111 222 333) |  | Subcontract Sum | 240000
Subcontractor |  | Ridgeline Facades Pty Ltd (ACN 444 555 666) |  | Prepared By | Vettex Pty Ltd – Chris Coyle
Departures Proposed |  | 2 |  | Response Requested By | 2026-09-25
SUBCONTRACT POSITION AND PROPOSED DEPARTURES | [5 empty] | FOR BUILDER COMPLETION
Item Ref # | Relevant Area | Clause | Current Subcontract Position | Subcontractor's Proposed Position | Basis of Request | Builder Response | Builder Comments
80 | Body Clause | Cl. 10.9 – Payment of Tax Invoice | 'The Tax Invoice is payable by Northline within the period specified in the Contract Particulars.' The Contract Particulars specify the Tax Invoice is payable on the last day of the calendar month following the month in which the Progress Claim is made. | Replace 'The Tax Invoice is payable by Northline within the period specified in the Contract Particulars.' with 'The Tax Invoice is payable by Northline within 30 days of receipt, consistent with the Trade Contractor's tendered payment terms.' | Tender qualification: '30 days from invoice.'
213 | Annexure/Schedule | Schedule 1 Item 28 – Liquidated Damages | (a) $5,000 per day for failure to achieve Works Completion; and (b) an additional $5,000 per day for delay to Head Contract Practical Completion. No aggregate cap. | Replace '(a) $5,000 per day; or (b) $5,000 per day.' with '(a) $120 per day (being 5% of the Contract Price pro-rated over 100 days); and (b) Nil. Total LDs payable under this Trade Contract shall not exceed $12,000 (5% of the Contract Price). Liquidated damages are the sole and exclusive remedy of Northline for delay in achieving Works Completion.' | Tender qualification: 'Will not accept liquidated damages above 5% of subcontract sum'.
BUILDER SIGN-OFF
Departures marked Accepted or Accepted as amended are to be incorporated into the subcontract by formal amendment before Ridgeline Facades Pty Ltd executes. Returning this schedule does not of itself amend the subcontract.
For and on behalf of Northline Constructions (Vic) Pty Ltd |  |  |  | Issued by
Name |  |  |  | Prepared by | Vettex Pty Ltd
Position |  |  |  | Contact | Chris Coyle, Director
Signature |  |  |  | Email | chris@vettex.com.au
Date |  |  |  | Document | VTX-HARROW-CSS-001 · Revision A
This schedule records the Subcontractor's proposed departures from the subcontract documents issued for the Project. Quoted wording is reproduced from those documents. Commercial positions only — not legal advice.

## How to Complete
How to complete this schedule
Harrow Street — FC01 Facade Cladding Package
VTX-HARROW-CSS-001 · Revision A · Response requested by 25 September 2026
Three steps
1. Work through the Commercial Summary tab. The two right-hand columns are the only cells open for editing — everything else is locked so the recorded positions cannot be altered by accident.
2. Pick a Builder Response against each item from the drop-down, then use Builder Comments for any qualification or alternative wording.
3. Complete the Builder Sign-off block at the foot of the schedule and return the file to chris@vettex.com.au by 25 September 2026.
What each response means
| Accepted | The proposed wording is agreed and will be incorporated by amendment before execution.
| Accepted as amended | Agreed in principle, subject to the alternative wording recorded in Builder Comments.
| Rejected | Not agreed. Please record the reason so the item can be closed out or escalated.
| Further discussion required | Needs a call before either party commits. Note who to contact.
Document control
| Reference | VTX-HARROW-CSS-001
| Revision | A
| Prepared | 18 September 2026
| Response requested by | 25 September 2026
| Prepared by | Vettex Pty Ltd — Chris Coyle, chris@vettex.com.au
| Departures proposed | 2